## Plan
DP Plan | [7 empty] | Start: | 2026-03-04 | Now: | 2026-03-18
Task | Category / Workstream | Status | Baseline Start | Baseline End | Forecast Start | Forecast End | Key Milestone | Risk Flag | Notes / Comments | Vendor | Calendar
Alpha | Build | Done | 2026-01-05 | 2026-01-16 | 2026-03-02 | 2026-03-13 | N | N |  | Acme | x
Beta | Build | In Progress | 2026-01-19 | 2026-01-30 | 2026-03-16 | 2026-03-27 | N | Y |  | Acme | x
Gamma | Test | Not Started | 2026-02-02 | 2026-02-13 | 2026-04-01 | 2026-04-10 | Y | N |  | Acme | x